## Sheet1
Sr.No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Diya | 2025-10-28 | OpenCV C++ extension threw errors on Windows due to missing OpenCV worker binaries required for ANPR. | Sprint 1 | Backend Team | Technical | Added missing OpenCV worker files into the workers directory, reconfigured environment, and reinstalled OpenCV | 2025-10-28 | Closed | Windows-specific OpenCV compatibility fix.
2 | Backend Team | 2025-11-01 | ANPR model file (.pb) failed to load because the model path pointed to an incorrect directory | Sprint 1 | Backend Team | Technical | Updated the correct full path to the model and added error handling for missing model files. | 2025-11-01 | Closed | Path mapping error corrected.
3 | Backend Team | 2025-11-04 | ATCC incorrectly counted some vehicles twice during frame transition points. | Sprint 2 | Backend Team | Functional | Implemented unique tracking IDs and applied frame-based filtering to avoid duplicate counts. | 2025-11-04 | Closed | Significantly improved accuracy
4 | Frontend Team | 2025-11-08 | Upload option wasn’t responding because the JavaScript fetch request targeted an invalid URL | Sprint 3 | Frontend Team | UI | Updated the correct request endpoint and configured CORS to allow frontend communication. | 2025-11-08 | Closed | Frontend integration fixed.
5 | Backend Team | 2025-11-12 | Server crashed while processing large video files due to memory overload | Sprint 4 | Backend Team | Performance | Increased file-size handling limit, added stream-based processing, and optimized memory usage. | 2025-11-12 | Closed | Stable for large uploads.
6 | Frontend Team | 2025-11-16 | Dashboard output wouldn’t refresh after processing ANPR/ATCC updates. | Sprint 3 | Frontend Team | UI | Added auto-refresh script logic and improved success callback to update results dynamically | 2025-11-16 | Closed | Real-time updates functional.